## TestCase
[11 empty] | TOTAL | #REF!
TC-ID | Module | Type of Testing | Features | Test Case | Exepected Result | Actual Result | preconditions | Reproducing Steps | Bugs Screen Shot | Severity |  | Remarks
0
1 | Sell | UI/UX | Screen Load | Sell screen UI loads properly | All UI elements load without crash | Found as per expectation. | User logged in | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.select বেচা" 5.observe the final result |  | medium | Passed
2 |  | UI/UX | Help UI | Help (?) icon is visible in the next page(দ্রুত বিক্রি করুন) | help icon should visiable properly | Found as per expectation. | Sell screen is fully loaded | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.notice right side of header in বিক্রি করুন" স্ক্রিন |  | Low | passed
3 |  | Functional | Help Video | Help video plays on tap | help video should plays after tapping on vedio | Found as per expectation. | Internet connection is active | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.notice right side of header in বিক্রি করুন" স্ক্রিন 6.click on help icon |  | medium | Passed
4 |  | UI/UX | button | দ্রুত বিক্রি button is visiable on this screen. | দ্রুত বিক্রি button should visiable on sell page | Found as per expectation. | Sell screen is loaded completely | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.notice left side of header in বিক্রি করুন" স্ক্রিন |  | Low | Passed
5 |  | UI/UX | Product List View | product list button is visible | product list button should visiable properly | found as per expectation. | Sell screen is loaded completely | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.notice right side bellow header |  | Low | Passed
6 |  | UI/UX | Search | Product search bar option is visible proparly on screen | Button is visible | Found as per expectation. | Sell screen is loaded completely | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.notice bellow product list and দ্রুত বিক্রি করুন button |  | Low | Passed
7 |  | UI/UX | Scanner | Scanner icon is visible beside search bar | Scanner icon is visible | Found as per expectation. | Sell screen is loaded completely | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.notice beside search bar |  | Low | Passed
8 |  | UI/UX | Product List | Product list displays correctly | Product name and price shown | Found as per expectation. | Sell screen is loaded completely | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.notice right side bellow header 6.click on product list 7.see the result |  | Medium | Passed
9 |  | Functional | Quantity Change | Product quantity can be adjusted | Quantity increases/decreases properly | Found as per expectation. | At least one product exists in inventory | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.click on test product 6.click on arrow 7.try increases or decreases |  | High | Passed
10 |  | Functional | Manual Add | পণ্য যুক্ত করুন manually adds product | New product form appears | Found as per expectation. | have to click add product | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.click on add product 6.fill up the form |  | Medium | Passed
11 |  | Functional | Advanced Info | Advance information is accessable for seller | Detailed input area is shown | Found as per expectation. | loaded in পণ্যের অ্যাডভান্স তথ্য screen | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.click on add product 6.scroll bellow 7.fillup the form |  | Low | Passed
12 |  | UI/UX | Cart Total | Total price shows ০ টাকা initially | total shows “০ টাকা” | Found as per expectation. | not yet select product | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.notice bellow in বিক্রি করুন page |  | Low | Passed
13 |  | Functional | Cart Calculation | Sell without selecting product not allowed | Error shown / Sell not processed | Found as per expectation. | Add any product | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.do not select any product 6.see the result |  | medium | Passed
14 |  | Functional | Validation | Cart updates total afteradding product | subtotal updates correctly | Found as per expectation. | No product added | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.click add product 6.fillup the product details 7.save 8.back previous page 9.click on any product 10.notice botom right side |  | High | Passed
15 |  | Functional | Customer Optional | Sell without customer name still allowed | Sell completes successfully | Found as per expectation. | Product added, no customer name | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.click add product 6.fiillup details 7.save and see the result |  | Low | Passed
16 |  | Functional | Product Search | Scanner input searches product | Matching product shown | not execute | Tap scanner and scan valid code | not execute |  | Medium | Passed
17 |  | Functional | Filter Function | Filter inside search bar works | Only products tagged under the selected category should be shown. There should be an option to reset/clear the filte | Not found as per expection | Tap on filter | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.go to the search bar right side 6.click on filter | filter error.jpg | Medium | Failed
18 |  | Functional | search | search bar is work properly when search the product after adding the list | Search bar should work properly | Found as per expectation. | user active on scrren | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.go to the search bar 6.search the product |  | medium | Passed
19 |  | Functional | Product add | Product stock count updates correctly when adding to cart | Stock should decrease by 1 per add; must never go negative; addition blocked once stock is zero | Not found as per expection | have to add product | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.click add product 6.add many products 7.see the behaviour | product stock count error.jpg | High | Failed
20 |  | Functional | payment | payment system work properly | Payment system sould work correctly | Found as per expectation. | add products | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.click add product 6.fill up advance information 7.select payment method 8.enter amount 9.see the result |  | Critical | Passed
21 |  | Functional | Quick Sell | দ্রুত বিক্রি করুন process work correctly | complete successful | Found as per expectation. | no info | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.click quick sell 6.enter all information and save 7.click user icon 8.search customer |  | Low | Passed
22 | Sales Book | UI/UX | screen loads | Sales Book screen loads properly on screen | Salse book screen should load proparly | Found as per expectation | User taps on "Sales Book" tab | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.see the result |  | Medium | Passed
23 |  | UI/UX | summary action | Current date and total sales amount are shown in a clean format | date and summary should display correctly | Found as per expectation | At least one previous sale exists | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5. notice bellow the header |  | Low | Passed
24 |  | UI/UX | filter tabs | Filter Tabs are visible | all filter tabs should visiable | Found as per expectation | Sales Book screen is fully loaded | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.see the result |  | Low | Passed
25 |  | Funtional | tabs | Tabs are clicable (day,week,month,year,custom) | all tabs are clicable | Found as per expectation | Tabs are present | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.click all tabs |  | Medium | Not Executed
26 |  | Funtional | tabs | all tabs are work proparly after selling product | all tabs should working properly | found as per expection | Filtered data exists | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.click all tabs one by one 6.see result |  | medium | Passed
27 |  | UI/UX | search bar | search bar screen load properly | Search bar should load properly | Found as per expectation | Filtered data exists | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.observe search bar is load or not |  | Low | Passed
28 |  | Funtional | search | search bar works correctly | Search bar should work perperly with proper information | Found as per expectation | Sales Book screen is loadedUser is logged in | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.Go to the search bar 6.enter coustomer name |  | Medium | Passed
29 |  | Funtional | search | only save customer information will show ,when search customer name | show will just save customer information | Not Found as per expectation | At least one customer was saved previouslyxt | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.Go to the search bar 6.search save customer name 7.again search random customer name 8.check every tab | accept all customers .jpg | High | Failed
30 |  | UI/UX | Learning | learning vedio section is visiable on screen | initially “চলুন শিখে নেই” section with thumbnail or video visible | Found as per expectation | App is opened fresh or no sales yet | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা |  | Low | Passed
31 |  | Functional | Vedio action | whenTapping help icon video opens | Vedio should open after clicking in vedio | Found as per expectation | Internet is on, video URL is available | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.click on help icon |  | Medium | Passed
32 |  | Functional | Export buttonButton | transaction information should available in the PDF. | pdf works properly. | Found as per expectation | Transaction history exists | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.click pdf in header |  | Medium | passed |  | Failed
33
33 |  | UI/UX | help | Help video icon (?) is visible on header part | help video ichon should visiable | Found as per expectation | Sales Book screen is fully loaded | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.notice right side of header |  | Low | Passed
34 |  | Functional | payment | all payment system process should acceptable like, phone number and QR code | both are should accepted | not Found as per expectation | Payment settings allow both | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.click sales product 6.select product 7.click on cart 8.enter quantity and others if need 9.go ahead 10.select bkash or nagad 11.click every system and see result | bkash phone number missing .jpg | Low | Failed
35 |  | Functional | Receipt | receipt share should be successful | receipt share successfull | Found as per expectation | Sale is completed, and sharing option is tapped | 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.click on any product 6.click on cereipt share option 7. select any option 8.send |  | Medium | Passed
69
70
71
72
73
74
75
76
77
78
79
80
81
82
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Bug Report
Bug Reporting
#SL 01
Issue: Filter option beside the search bar is not working
Reproducing Steps:
1.Open hisabee business app
2.login with proper information
3.go to dashboard
4.click on বেচা"
5.go to the search bar right side
6.click on filter
Module: sell
Priority: P0
Severity: Medium
Screenshot:filter error.jpg
Expected:Only products tagged under the selected category should be shown. There should be an option to reset/clear the filte
Actual:After clicking filter option it do not show any tag unter the selected catagory.
Responsible QA: Fatema
Bug Reporting
#SL 02
Issue: Product stock count error.
Reproducing Steps:
1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচা" 5.click add product 6.add many products 7.see the behaviour
Module: sell
Priority: P0
Severity: High
Screenshotproduct stock count error.jpg
Exepected Result :AStock should decrease by 1 per add; must never go negative; addition
blocked once stock is zero
Actual: when add pruct to cart it do not maintain decrease order.
Responsible QA: Fatema
Bug Reporting
#SL 03
Issue: accepting random customer names
Reproducing Steps: 1.Open hisabee business app 2.login with proper information 3.go to dashboard 4.click on বেচার খাতা 5.Go to the search bar 6.search save customer name 7.again search random customer name 8.check every tab
Module: sales book
Priority: P0
Severity: high
screenshotaccept all customers .jpg
Expected: show will just save customer information or existing customer information
Actual: accepting any random customer names also.
Responsible QA: Fatema
Bug Reporting
#SL 04
Issue: QR-based payment available, but no manual phone number entry for bKash or Rocket
Reproducing Steps:
1.Open hisabee business app
2.login with proper information
3.go to dashboard
4.click on বেচার খাতা
5.click sales product
6.select product
7.click on cart
8.enter quantity and others if need
9.go ahead
10.select bkash or nagad
11.click every system and see result
Module:sales book
piority:p0
severity:medium
Screenshot:bkash phone number missing .jpg
Expected:both are should accepted like phone number and QR code
Actual:there have no option enter phone number for payment manually.
Responsible QA: Fatema
Bug Reporting